***‘Health @ 2020’***

**Faculty of Health Academic Planning Cycle 2014/15**

**Fall Term 2014: Building Blocks**

* **Ongoing**: Preparation work on critical areas, such as Strategic Enrollment Management (SEM), at monthly meetings of Chairs & Directors and the Executive & Planning Committee
* **November 1**: Academic and Administrative Program Review (AAPR) results for our 37 Academic and Administrative programs ranked for a) **Quality** and b) financial **Sustainability**
* **November 26**: Planning Retreat involving 33 senior leadership: Dean, Associate Deans, Chairs, Masters, UPDs, GPDs, EO & Administrative Directors
* **December**: form the Guiding Coalition (Executive & Planning Committee) and ‘Plan the Plan’ regarding details of the process for the academic and resource planning exercise slated for January – April

**Winter Term 2015: Creating the Plan**

* + **January - April**: Generate a Draft Health 2015-2020 Academic Plan: consultation meetings with Schools/Department and ORUs, task group reports: a) Teaching & Learning Strategy (S. Murtha lead), b) Research Strategy (W. Gage lead), c) Community Strategy (M. Wiktorowicz lead), d) Global Health Strategy (M. Wiktorowicz lead), e) Integrative Health (A. Belcastro & J. Goldberg co-leads), Faculty and School Council meetings, meet with student leaders, external stakeholders, others
	+ **March 2:** AAPR Planning Response document submitted to the Vice-President & Provost which focused on our strengths and challenges, strategies for doing things differently, and opportunities for sustaining our academic programs and generating new revenue
	+ **March-April**: New Shared Accountability and Resource Planning (SHARP) budget model made public with a three year phased implementation for 2017/18
	+ **April 29**: All day Forum at Black Creek Pioneer Village (facilitated by M. Pitters) involving approximately 80-90 people (faculty, staff, students) to review and polish the Draft Plan
	+ **May 6**: Presentation and adoption of the Health 2015-2020 Academic Plan at our Faculty Council meeting
	+ **May:** Operationalize strategic directions, actions and outcomes in Health’s 2015-2016 Integrated Resource Plan (IRP)
	+ **May - June**: Review the Plan with senior leadership: Rhonda Lenton: Vice President & Provost, Robert Hache: Vice President Research & Academic, Garry Brewer: Vice President Finance & Administration, Jeff O’Hagan: Vice President Advancement and President Mamdouh Shoukri
	+ **July 1, 2015**: Implement ‘Health @ 2020’ Academic and Integrated Resource Plan (IRP)